8 Million Reasons to Read in NYC

Toolkit Template

Event/Activity:     Family Literacy Night – TOUR THE STATES THROUGH LITERATURE

Audience:   Parents and students				Grade(s): Elementary

Partners:   Parent Coordinator, Parents’ Association, Public Librarian, Staff, Volunteers

Goal(s): To share literature from different parts of the US as we TOUR THE STATES THROUGH LITERATURE

To share a wide variety of literature through read aloud and dramatization.

Resources:  Public library, school library, parents’ association, staff, parent coordinator, and volunteers and possible non-profit groups

Activities: Families will TOUR THE STATES THROUGH LITERATURE by visiting classrooms that have been designated as states.  Each classroom will represent another state or region of our country that they have researched and learned about. Each classroom will be decorated accordingly.  There will be a “State Reader” in each room that will read aloud a story that is representative of the state or region.   Each family will have a map of the US that they will color in as they visit each state.  Families who have visited at least five states will receive a special prize (book marks, books, coloring books, pencils, erasers, etc.).  They will also receive a certificate that they have completed the journey.

Timeline:

- Develop a team to coordinate all essential activities such as recruitment, advertising, communication, research and literature activities by individual classrooms, refreshments, volunteers, flyers, supplies, give-aways, etc.

- Meet with team to brainstorm means for funding event.

- Create a calendar with event dates and meeting schedule.

- Select individuals and their responsibilities.

- Recruit volunteers for read alouds and other administrative activities.

- Secure necessary materials, refreshments and supplies.

- Develop flyers and other promotional material.

- Select literature that will be used at read alouds.

- Check RSVPs.

- Create a tour for different family groups using different color sheets.

- Final week – coordinate all aspects of event – check on classroom progress, refreshment committee, volunteer readers, deliver materials and supplies

Communication/Promotion:

- Send out an initial ‘SAVE THE DATE’ flyer.

- Send out flyer for volunteers and readers.

- Contact local business for possible donations.

- Create countdown posters.

- Letters to staff and parents announcing and explaining activities.

- Contact local newspaper.

Evaluation/Documentation:

Photographs

Newsletter and local newspaper articles

Event evaluation worksheet

Post a list of families that have completed the tour.

Follow-up meeting of original team.